## Progress
Water & Sanitation Project -2018
Physical and Financial Progresss -2018
Divisional Secretariat Division :- Padavi-Sripura
2018.09.05
S. No | Benificary Name | G.N.Division | Financial Progress |  |  |  | Physical Progress | [6 empty] | Remarks
|  |  | Total Estimate | A | B | C | A | B | C | D | E | F | G
1 | N.prasanna lakmaal | Singapura | 54500 | A: 14500; B: 20000; Physical Progress D: √
2 | W.W.M.Karunarathna | Singapura | 54500 | A: 14500; B: 20000; C: 20000; Physical Progress G: √
3 | Y.N.Ranjith Premarathna | Singapura | 54500 | A: 14500; B: 20000; C: 20000; Physical Progress G: √
4 | R.P.B.D.Rajapaksa | Singapura | 54500 | A: 14500; B: 20000; C: 20000; Physical Progress G: √
5 | R.D.K.K.Rajapaksa | Singapura | 54500 | A: 14500; B: 20000; Physical Progress D: √
6 | M.Pathmini Siriyalatha | Singapura | 54500 | A: 14500; B: 20000; Physical Progress E: √
7 | H.M.Nihal Karunarathna | Paranamathawahciya | 54500 | A: 14500; B: 20000; Physical Progress D: √
8 | G.P.H.K.Nuwan Srilaal | Paranamathawahciya | 54500 | A: 14500; Physical Progress C: √
9 | W.A. Somapala | Paranamathawahciya | 54500 | A: 14500; B: 20000; C: 20000; Physical Progress G: √
10 | M.H.Sarath Gunarathna | Paranamathawahciya | 54500 | A: 14500; B: 20000; Physical Progress F: √
11 | S.M.Lokkumenike | Paranamathawahciya | 54500 | A: 14500; Physical Progress F: √
12 | B.Premawathy | Paranamathawahciya | 54500 | A: 14500; B: 20000; C: 20000; Physical Progress G: √
13 | R.M.Rathnayake | Paranamathawahciya | 54500 | A: 14500; B: 20000; Physical Progress E: √
| Total Allocation |  | 708500 | A: 188500; B: 220000; C: 100000
| Discription for Rating |  |  | A: Rates; B: Percentage Ranges; Physical Progress B: No; Physical Progress C: Financial Progress; Physical Progress G: Amount
| Estimate is being / to be prepared and initial work stared |  |  | A: A; B: (0-5)%; Physical Progress B: A-; Physical Progress C: First Payment; Physical Progress G: 14500
| Construction:-Estimates prepared and approved, Bid docoments prepared, Quatations called, Tende awarded. (25% completed) |  |  | A: B; B: (6-25)%; Physical Progress B: B-; Physical Progress C: Secound Payment; Physical Progress G: 20000
| Construction:-Started construction work (40% completed) |  |  | A: C; B: (26-40)%; Physical Progress B: C-; Physical Progress C: Last payment; Physical Progress G: 20000
| Construction:-60% completed |  |  | A: D; B: (41-60)%
| Construction:-80% completed |  |  | A: E; B: (61-80)%
| Construction:-99% completed |  |  | A: F; B: (81-99)%
| Construction:-100% completed |  |  | A: G; B: 100%
Prepared By: - Checked By: - Recommended By: - Approved By: -